## July 19-Sep 19
July 19-Sep19
Date Sch | Status | Application Date (WX-800) | Applicant Name | Application Number | Total Priority Points | Housing Type | Is unit owned or rented? | County | Phone Number | Street Address | City | Notes
| completed Jul 19 |  | Client A | 111 | 42 | house | own
| completed Aug 19 |  | Client B | 121 | 40 | mobile | own
| in-progress |  | Client C | 131 | 39 | mobile | rent
| deferred Aug 19 |  | Client D | 141 | 37 | house | own
| in-progress |  | Client E | 151 | 36 | house | own
|  |  | Client F | 161 | 34 | mobile | own
|  |  | Client G | 171 | 31 | house | rent
Explanations: Clients A & B were added to the list and was completed during the quarter. Clients C &E are currently in progress. The completion date will be listed when finished. Client D was deferred. Clients F &G have not yet been served and will be carried over to the next list.

## Oct 19-Dec 19
Oct 19-Dec 19
Date Sch | Status | Application Date (WX-800) | Applicant Name | Application Number | Total Priority Points | Housing Type | Is unit owned or rented? | County | Phone Number | Street Address | City | Notes
| completed Oct 19 |  | Client H | 181 | 40 | house | own
| in progress |  | Client I | 191 | 39 | house | own
| completed Oct 19 |  | Client E | 151 | 36 | house | own
| in progress |  | Client F | 161 | 34 | mobile | own
|  |  | Client G | 171 | 31 | house | rent
Explanations: Client H was added to the list and completed during the quarter. Client I is in progress. Client E was carried over to this list from the previous quarter because the work was not yet finished before it was time to reprioritize. Client E is now completed. Client F is in progress. Client G has not been served and will be carried over to the next list. (Clients F &G were also carried over from the previous list).

## Jan 20-Mar 20
Jan 20-Mar 20
Date Sch | Status | Application Date (WX-800) | Applicant Name | Application Number | Total Priority Points | Housing Type | Is unit owned or rented? | County | Phone Number | Street Address | City | Notes
|  |  | Client J | 200 | 37 | mobile | own
|  |  | Client G | 171 | 31 | house | rent
|  |  | Client K | 201 | 29 | house | own
Explanations: Client J was added to the list and will be first to be contacted for an evaluation. Client G was carried over from the previous list, but because he hadn't received services before the quarter was over, he is now second and should not be contacted before Client J. Client K will be next after Client G to be contacted for an evaluation.

## Apr 20-June 20
Apr 20-June 20
Date Sch | Status | Application Date (WX-800) | Applicant Name | Application Number | Total Priority Points | Housing Type | Is unit owned or rented? | County | Phone Number | Street Address | City | Notes